## Slide 1: COMMUNITY DEVELOPMENT THROUGH SOCIAL ENTREPRENEURSHIP
LESSONS LEARNED

## Slide 2: THE PROJECT AND THE IDEA…
60 community groups NGOs from disadvantaged regions of Armenia (mostly from rural communities) has taken part in SE introductory courses and got acquainted with the project.
27 Community groups and regional NGOs has taken part in a year-log educational process (e-learning and face-to-face) and developed their SE business plans.
10 Selected enterprises got funding for establishment of their start-ups and further consultancy and mentoring services.
500 Community groups and regional NGOs has taken part in a stand-alone e-course on Social Entrepreneurship
Armenian Social Enterprise association is empowered and grown from 7 to 28 members, and facilitates the creation of a State concept on SE
The project is funded by European Commission
The project is co-funded by Austrian Development Agency

## Slide 3: WHY social Enterprises?
Serious problems of current economic schemes
Changes in the approaches of Donor Community
Periodical Crisis situations in the World Economic System,
Assessments of the efficiency of the International Support Schemes
The COSTS of donor dependency
Polarization/gapes in NGO sector
SE
The failure of most of the governments and donors to solve local community issues
Eurasian developments in CIS

## Slide 4: LESSON 1 : Problem of definition
Although it is a long while the concept is under discussion still no common definition accepted by all actors
100.000 definitions starting from “APPLE as Social Enterprise” Finishing with very narrow definitions
OUR DEFINITION:
“Social entrepreneurship is an entrepreneurial activity, which puts the solution of a social problem at the core of its business model, and which dedicates most of its profit to positive social transformation and solution of social challenges”

## Slide 5: LESSON 2: Difficulty to explain the Model of Functioning
Social Enterprise
Products and Services
Income
Expenses
Generation of Profit
Social Impact
Payback to Investors
Community development
Re-Investment in the of SE

## Slide 6: LESSON 3 : SOCIAL IMPACT of SE
SE
IMPACT
On you
On your family
On your friends
On your community
On your country
On the Planet
Working on maximal social impact !!
Planning the Impact
Measuring the Impact
Presenting the impact
The impact of the business
Social Issue 2
Social Issue 1
The profit directed to social Impact
Social Issue 4
Social Issue 3
Social Issue 1

## Slide 7: LESSON 4 : SOCIAL INNOVATION
Innovation
Global
Innovation
National
Innovation
Local

## Slide 8: LESSON 5 : Scalability and Replicability
Small
Bigger
VEEEERY big
?
Is it necessary to scale up ?

## Slide 9: LESSON 6 : Value Capsule and the SOCIAL ENTREPRENEUR
Why should I limit myself ?

## Slide 10: LESSON 7 : WHY SO MANY FAILURES?
There were millions of Euros spent before us… Where are the success stories?
THE Importance of the experience of the “work with the soil”: Sterile NGOs and Bureaucracy in Donor Agencies
The lack of :
“I REALLY DO WANT this to happen” approach
Complexity of the topic: multidisciplinary nature and mentality crash

## Slide 11: Some “provocations”
Provocation no. 2  !!!
Some researchers/futurologists state that
Social Entrepreneurship is the future of all the NGOs…
Provocation no. 1  !!!
Some researchers/futurologists state that
Social Entrepreneurship is the future of all the Businesses…

## Slide 12: We will be happy to cooperate with you!!!
Additional Information:
www.SE.center